## Sprint Plan
Sprint | Name | Goal | Features | System Design | Scalability Focus | Testing Checklist
1 | Foundation & Auth | Secure base system | Supabase auth, Google login, sessions | Next.js + Supabase auth layer | Stateless auth, secure sessions | Login, refresh session, route protection
2 | Database Schema | Robust data layer | Tables, relationships, RLS | Normalized PostgreSQL schema | Indexed queries, relational integrity | Insert/query test, RLS validation
3 | Task System | Core execution engine | Task CRUD, deadlines | API-based task handling | Index on deadline, pagination-ready | CRUD ops, load test
4 | Habit Tracker | Time-series tracking | Habits, logs, streaks | Separate logs table | Efficient date queries | Streak accuracy test
5 | Dashboard | Data aggregation | Unified dashboard API | Single endpoint aggregator | Reduce API calls | <1s load time
6 | Journal + AI | AI integration | Journal, summary, mood | Async AI processing | Cache AI outputs | AI quality, rate limits
7 | Notes + AI | Knowledge system | Notes, summaries | Reusable AI endpoints | Avoid duplicate AI calls | Summary correctness
8 | Project Tracker | Complex workflows | Projects + tasks | Relational mapping | Efficient joins | Project-task integrity
9 | Public Schedule | Controlled sharing | Public profile page | Filtered API exposure | Secure data exposure | Privacy validation
10 | UI Polish | Premium UX | Glass UI, animations | Component system | Lightweight UI | Responsiveness
11 | Performance | Optimization | API tuning, caching | Optimized queries | Reduced DB calls | Load testing
12 | Flexibility | Future-proofing | Feature flags, configs | Modular services | Scalable architecture | Config testing